## Myself
SSIS in ADF Configuration
Task Updates
Date | Feature | Description | Status | Deadline | Blockers / Comments
26/08/2019 | Biilion DB | Fimilarising myself with db and tables | Completed | 28/08/2019 | No
2019-10-09 | ANT BI Staging database | Creating Staging DB to load ANT data model before commiting data to ANT Datawarehouse | Completed | 2019-10-09 | no
2019-10-09 | ANT BI Datawarehouse | Creating datawarehouse db and Dim Tables | Completed | 2019-10-09 | No
2019-10-10 | Excel Date table | Creatining Date table in Excel | Completed | 2019-10-09 | No
2019-10-09 | ETL DimDate | DimDate ETL package | Completed | 2019-10-09 | No
2019-11-09 | DimGroup Table | Created DimGroup table | Completed | 19/9/2019 | No
20/09/2019 | DimDate ETL package | Created Lara BI shared folder and Uploading DimDate ETL package screen shot | Completed | 20/09/2019 | No
21/09/2019 | DimLibrary Package | ETL DimLibrary package | Done |  | No
2019-03-10 | DimDate table, DimLocation table, DimLibrary - ETL package | Reworked DimDate, DimLocation and DimLibrary tables , and amended DimLibrary ETL package | Done | 2019-03-10 | No
2019-03-10 | DimGroup ETL package | Working on ETL Package | Done | 2019-07-10 | No
2019-03-10 | DimUser ETL package | Working on ETL Package | Done | 2019-07-10 | No
3696143 | DimGroup ETL Package | Updated ETL Package | Done | 2019-09-10 | No
2019-09-10 | DimUser ETL package | Working on updating ETL Package | Done | 2019-10-10 | No
2019-10-10 | DimLibrary ETL package | Working on updating ETL Package | Done | 2019-10-10 | No
2019-10-10 | Fact_MeetingAttendance | Creating DW table in SQL Server | Done | 2019-10-10 | No
2019-10-10 | Fact_MeetingAttendance | ETL Package | Done | 30/10/2019
2019-10-10 | Fact_ScrumUpdate | Creating DW table in SQL Server | Done | 27/10/2019 | No
2019-10-10 | Fact_ScrumUpdate | Working on ETL Package | Done | 6//11/2019 | no
2019-05-11 | Updated ETL ProjectAntWD package | Created new ETL Package based on updated DW Table Structure document | Done | 2019-06-11 | Yes, lacking knowledge how to create a proper ETL package which can check for exitsing records in Dim Tables , insert new records and automaticaly propogate the changes to the Fact tables.
2019-05-11 | Power BI | Dashboard prototype | In progress | 22/11/19 | No
18/11/2019 | Reworking ProjectAnt Data Model | Identifying extra Dim tables | In progress | 18/11/2019 | No
28/11/2019 | FactUserGroupProgramProject | FactUserGroupProgramProject Data Model | Done | 28/11/2019 | No
| SSIS t | SSIS Package | Done | 28/11/2019 | No
| Data Model Spec | FactUserGroup Data Model Specification | Done | 28/11/2020 | No
| Power BI | Visualisation | In progress | 2019-02-11 | No
2019-03-12 | ProjectAnt - Human Dashboard | Creating Fact tables
2019-09-12 | ProjectAnt - Human Dashboard | Continue working on Facts tables | In progress | 2019-12-12 | No

## SindhuK
Task Updates
Date | Feature | Description | Status | Deadline | Blockers / Comments
26/08/2019 |  | Went through the DataBase tables structures and keys |  |  | No
28/09/2019 | DimUser | Creating the SSIS package using SCD type2 | Finish | 2019-09-02 | No
28/09/2019 | DimLibrary | Creating the SSIS package | Finish
29/09/2019 | DimGroup | Creating the SSIS package using SCD type1 | Finish
| DimLocation | Creating the SSIS package using SCD type0 | Finish
26/10/2019 | Dim date | Creating the SSIS package | Finish
27/10/2019 | Fact_Attendence | Created table in sql and created package in SSIS | Finish
| Fact_MeetingAttendence | Created table in sql and created package in SSIS | Finish
| Fact_UserReviews | Created table in sql and created package in SSIS | Finish
| Fact_MentorReviews | Created table in sql and created package in SSIS | Finish
| Fact_TechnicalAssesment | Created table in sql and created package in SSIS | Finish
| Fact_Scrumupdate | Created table in sql and created package in SSIS | Finish
2019-06-11 | Fact_UserLibrary | Created table in sql and created package in SSIS | Finish | 2019-11-11 | No
2019-11-11 | PowerBI | Taking the Datawarehouse into powerBI | InProgress | 13/11/2019 | No
13/12/2019 | PowerBI | Creating some Reports in PowerBI | InProgress | 18/11/2019

## ShaniP
Task Updates
Date | Feature | Description | Status | Deadline | Blockers / Comments
25/08/2019 | BillionReplication DB | Familarising myself with DB and Tables structure, keys and referencing
27/08/2019 | Staging Area | Creating Staging Area and developing ETL | Completed | 2019-09-03 | No
29/08/2019 | DimGroup | Creating Group Dimention and developing ETL, SCD1 | Completed | 2019-09-03 | No
29/08/2019 | DimUser | Creating User Dimention and developing ETL, SCD1+SCD2 | Completed | 2019-09-04 | No
2019-04-09 | DimLocation | Creating Location Dimention and developing ETL, SCD0 | Completed | 2019-09-06 | No
2019-09-11 | DimLibrary | Creating Library Dimention and developing ETL, SCD0 | Completed | 2019-09-11 | No
2019-09-11 | DimDate | Loading DimDate | Completed | 2019-09-11 | No
28/09/2019 | Fact_Technical Assessment | Creating act_Technical Assessment and developing ETL | In progress | 2019-10-01 | No

## JusteenaP
Task Updates
Date | Feature | Description | Status | Deadline | Blockers / Comments
28/08/2019 | DimGroup |  | Completed | 2019-11-09
28/08/2019 | DimUser |  | In Progress
| FactMeetingAttantance |  | Completed
| DimLocation |  | Completed
| DimLibrary |  | Completed
| DimDate |  | Completed
| FactAttantance |  | Completed
| FactUserReview |  | Completed | 29/10/2019
| Fact_MentorReview |  | Completed | 30/10/2019
| Fact_TechnicalAssement |  | Completed | 2019-05-11
| Fact_ScrumUpdate |  | Completed
| Fact_UserLibrary |  | Completed
| FactMeetingAttantance |  | Completed

## Jane
Task Updates
Date | Feature | Description | Status | Deadline | Blockers / Comments
2019-04-11 | Created a lock version of Bilion DW |  | Done
2019-06-11 | Creating DimGroup tbl and ETL |  | Done
2019-07-11 | Creating DimLocation and ETL |  | Done
2019-07-11 | Creating DimLibrary and ETL |  | Done
2019-07-11 | Creating DimDate |  | Done
2019-08-11 | Creating DimUser and ETL |  | Done
2019-08-11 | Creating Fact_Attendance |  | Done
2019-10-11 | Creatinf Fact_MeetingAttendance |  | Done
14/11/2019 | Creating Fact_ScrumUpdate, Fact_UserLibrary, Fact_TechnicalAssessment |  | Done